## Instructions
TEAM NAME | 43
PROJECT NAME | Tools for Speech Recognition
PROJECT MENTOR | Khyathi Raghavi
TEAM MEMBERS | Shivam Khandelwal
Adhish Singla
Nitish Jain
Romil Aggarwal

## Team_Status
TEAM NAME | 43
PROJECT NAME | Tools for Speech Recognition
PROJECT MENTOR | Khyathi Raghavi
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 4 (Aug 25 – 31)
Learn PyQt | Preparation | Adhish | 4 | 7 | Done | Using IDEs can make our job easier | -3 | 42.8571
Learn Scrappy | Preparation | Shivam | 2 | 3 | Done |  | -1 | 33.3333
Learn about Noise reduction | Preparation | Nitish | 1 | 4 | Done | Time increased as more parameters were given by Clients | -3 | 75
Project synopsis writeup | Documentation | Adhish | 1 | 0.5 | Done | Uploaded | 0.5 | 100
Identify role owners | Preparation | Romil | 1 | 1.5 | Done |  | -0.5 | 33.3333
Meetings organization | Coordination | Romil | 1 | 1.5 | Done | Meetings done | -0.5 | 33.3333
Status tracker | Documentation | Shivam | 2.5 | 3 | Done | Status Tracker updated for current week | -0.5 | 16.6667
Minutes of meetings | Documentation | Nitish | 3 | 4 | Done | Minutes of meetings for the week uploaded
Week 5 (Sept 1 - 7)
Learn Android (Basics) | Preparation | Romil | 7 | 8 | Done |  | -1 | 12.5
Basic GUI implimentation | Interfaces | Adhish | 4 | 3.5 | Done |  | 0.5 | 14.2857
Research existing tech. On NLP | Preparation | Shivam | 2 | 2.5 | Done | NLPK selected for the work | -0.5 | 20
Morph Analysis using NLPK | Development | Shivam | 0.5 | 1 | Done |  | -0.5 | 50
Minutes of meetings | Documentation | Adhish | 0.5 | 0.5 | Done |  | 0 | 0
Noise reduction using SOX and analysis | Development | Nitish | 4 | 3.2 | Done |  | 0.8 | 25
Research tech. To save data loss in sounds | Preparation | Shivam | 2 | 1.5 | Done
Week 6 (Sept 8 - Sept 14)
Learn Android (Related to recording) | Preparation | Romil | 4 | 3.5 | Done |  | 0.5 | 14.2857
GUI implimentation (File open) | Interfaces | Adhish | 2 | 2 | Done | File can be opened and displayed line by line | 0 | 0
Research websites to get sentances from | Preparation | Shivam | 0.5 | 1.5 | Done | Wikipedia + Some newspaper sites selected | -1 | 66.6667
Documentation (MoM+Status Tracker) | Documentation | Shivam | 0.5 | 1 | Done | (Previously written as SRS due to misunderstanding) | -0.5 | 50
Noise reduction using SOX and analysis (with different parametes) | Development | Nitish | 2 | 3 | Done | Work completed and selected by clients | -1 | 33.3333
Week7 (Sept 15 - Sept 21)
Basic Android Implementation GUI | Development | Romil | 4 |  | Done | Open and UI without functionalities
GUI implimentation (Voide Recording) | Development | Adhish | 5 | 4 | Done | File can be opened and displayed as it is. | 1 | 25
Scrappy implementation on Wikipedia | Development | Shivam | 2.5 | 3 | Done | Moved from Scrapy to html_dom_parser in php for better implementation. Clients have no problem | -0.5 | 16.6667
Website UI development (Tool2 – Website) | Development | Nitish | 5 |  | Done
Status tracker | Documentation | Shivam | 0.5 | 0.5 | Done | (Previously written as SRS due to misunderstanding) | 0 | 0
SRS | Documentation | Adhish | 4 | 5 | Done |  | -1 | 20
Minutes of meetings | Documentation | Romil | 0.5 | 1 | Done | MoM work to be done on last day of the week | -0.5 | 50
Week8 (Sept 22 - Sept 28)
Android Implementation GUI related to recording | Development | Romil | 2 |  | Done | Open and UI without functionalities
End Silence detection - Noise analysis | Development | Nitish | 6 | 5 | Done |  | 1 | 20
TestPlan | Documentation | Nitish | 3 | 3.5 | Done | updated in the repo | -0.5 | 14.2857
Crawling basic GUI + Running demo (manual running, not cron) | Development | Shivam | 9 |  | Done | (pending client verification scheduled 29th Sept)
Minutes of meetings | Documentation | Romil | 1 | 1.2 | Done | MoM work to be done on last day of the week | -0.2 | 16.6667
Status tracker | Documentation | Shivam | 0.5 | 0.5 | Done |  | 0 | 0
Voice Recorder | Development | Adhish | 6 | 5.5 | Done | implementation | 0.5 | 9.0909
Week9 (Sept 29 - Oct 5)
End silence detection with peaks | Development | Nitish | 2 | 3 | Done |  | -1 | 33.3333
GUI of the android app | Development | Romil | 3 | 3.5 | Done |  | -0.5 | 14.2857
Static Graph Preview | Development | Adhish | 5 | 5.5 | Done |  | -0.5 | 9.0909
CRON Implementation on Crawl Queue | Development | Shivam | 4 | 4.5 | Done |  | -0.5 | 11.1111
Design Document | Documentation | Adhish | 5 | 4.5 | Done |  | 0.5 | 11.1111
Status tracker | Documentation | Shivam | 0.5 | 0.5 | Done |  | 0 | 0
Week10 (Oct 6 - Oct 12)
checking for 32K frequency | Development | Nitish | 1.5 | 2 | Done |  | -0.5 | 25
recording and playing a file | Development | Romil | 2.5 | 3.5 | Done |  | -1 | 28.5714
Incorporate Graph with Recorder | Development | Adhish | 5 | 5.5 | Done |  | -0.5 | 9.0909
CRON Implementation on Sentance Queue | Development | Shivam | 2 | 1.5 | Done |  | 0.5 | 33.3333
Status tracker | Documentation | Shivam | 0.5 | 0.5 | Done |  | 0 | 0
Week11 (Oct 13 - Oct 19)
compatibility of voice analysis | Testing | Nitish | 2 |  | Ongoing
Replace Spectrometer by Graph Viewer | Development | Adhish | 2.5 |  | Planned
Dictionary structure | Development | Shivam | 3 |  | Planned
Status tracker | Documentation | Shivam | 0.5 |  | Done
re-factoring and r1 | Design | Romil | 8.5 |  | Ongoing

## Individual_Status
TEAM NAME | 43
PROJECT NAME | Tools for Speech Recognition
PROJECT MENTOR | Tools for Speech Recognition
Actvities | Shivam Khandelwal |  | Adhish Singla |  | Nitish Jain |  | Romil Aggarwal |  | 0 |  | Estimated Total Hours | Actual Total Hours
| Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent
Week 4 (Aug 25 – 31)
Learn PyQt | 0 | 0 | 3 | 5 | 0 | 0 | 1 | 2 |  |  | 4 | 7
Learn Scrappy | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2 | 3
Learn about Noise reduction | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 |  |  | 1 | 4
Project synopsis writeup | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 |  |  | 1 | 0.5
Identify role owners | 0.5 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | 1 | 1.5
Meetings organization | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 1 |  |  | 1 | 1.5
Status tracker | 1 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 2.5 | 3
Minutes of meetings | 1.5 | 2 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 |  |  | 3 | 4
Week 5 (Sept 1 - 7)
Learn Android (Basics) | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 |  |  | 7 | 8
Basic GUI implimentation | 0 | 0 | 3.5 | 3 | 0 | 0 | 0.5 | 0.5 |  |  | 4 | 3.5
Research existing tech. On NLP | 2 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2 | 2.5
Morph Analysis using NLPK | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 1
Minutes of meetings | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0.5
Noise reduction using SOX and analysis | 1 | 1 | 0 | 0 | 3 | 2.2 | 0 | 0 |  |  | 4 | 3.2
Research tech. To save data loss in sounds | 1.5 | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 0 |  |  | 2 | 1.5
Week 6 (Sept 8 - Sept 14)
Learn Android (Related to recording) | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 3.5 | 3 |  |  | 4 | 3.5
GUI implimentation (File open) | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 |  |  | 2 | 2
Research websites to get sentances from | 0.4 | 1 | 0 | 0 | 0.1 | 0.5 | 0 | 0 |  |  | 0.5 | 1.5
Documentation (MoM+Status Tracker) | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 1
Noise reduction using SOX and analysis (with different parametes) | 0.5 | 0.5 | 0 | 0 | 1.5 | 2.5 | 0 | 0 |  |  | 2 | 3
Week7 (Sept 15 - Sept 21)
Basic Android Implementation GUI | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  |  |  | 4 | 0
GUI implimentation (Voide Recording) | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0 |  |  | 5 | 4
Scrappy implementation on Wikipedia | 1.5 | 2 | 0 | 0 | 1 | 1 | 0 | 0 |  |  | 2.5 | 3
Website UI development (Tool2 – Website) | 1 |  | 0 | 0 | 4 |  | 0 | 0 |  |  | 5 | 0
Status tracker | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0.5
SRS | 0.5 | 0.5 | 1.5 | 2 | 1.5 | 2 | 0.5 | 0.5 |  |  | 4 | 5
Minutes of meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 |  |  | 0.5 | 1
Week8 (Sept 22 - Sept 28)
Android Implementation GUI related to recording | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | 2 | 0
End Silence detection - Noise analysis | 0 | 0 | 0 | 0 | 6 | 5 | 0 | 0 |  |  | 6 | 5
TestPlan | 1 | 1.5 | 0 | 0 | 2 | 2 | 0 | 0 |  |  | 3 | 3.5
Crawling basic GUI + Running demo (manual running, not cron) | 7 |  | 0 | 0 | 2 |  | 0 | 0 |  |  | 9 | 0
Minutes of meetings | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2 |  |  | 1 | 1.2
Status tracker | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 |  |  |  | 1 | 0.5
Voice Recorder | 0 | 0 | 6 | 5.5 | 0 | 0 | 0 | 0 |  |  | 6 | 5.5
Week9 (Sept 29 - Oct 5)
End silence detection with peaks | 0.5 | 1 | 0 | 0 | 1.5 | 2 | 0 | 0 |  |  | 2 | 3
GUI of the android app | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 2.5 | 3 |  |  | 3 | 3.5
Static Graph Preview | 1 | 1.5 | 3 | 3 | 0 | 0 | 1 | 1 |  |  | 5 | 5.5
CRON Implementation on Crawl Queue | 2.5 | 3 | 0.5 | 0.5 | 1 | 1 | 0 | 0 |  |  | 4 | 4.5
Design Document | 2.5 | 2 | 2.5 | 2.5 | 0 | 0 | 0 | 0 |  |  | 5 | 4.5
Status tracker | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0.5
Week10 (Oct 6 - Oct 12)
checking for 32K frequency | 0 | 0 | 0.5 | 0.5 | 1 | 1.5 | 0 | 0 |  |  | 1.5 | 2
recording and playing a file | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 2 | 3 |  |  | 2.5 | 3.5
Incorporate Graph with Recorder | 1 | 1.5 | 3 | 3 | 0 | 0 | 1 | 1 |  |  | 5 | 5.5
CRON Implementation on Sentance Queue | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2 | 1.5
Status tracker | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0.5
Week11 (Oct 13 - Oct 19)
compatibility of voice analysis | [10 empty] | 0 | 0
Replace Spectrometer by Graph Viewer | [10 empty] | 0 | 0
Dictionary structure | [10 empty] | 0 | 0
Status tracker | [10 empty] | 0 | 0
re-factoring and r1 | [10 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0